## Sheet1
Date | Month | Year | Project | Event | Filename
2 | January | 2024 | SVG | Stilt Floor Column Boxes | IMG_0155
3 | January | 2024 | SVG | Column Concreting for Stilt Columns | IMG_0159
| January | 2024 | SVG |  | IMG_0166
4 | January | 2024 | SVG | Deshuttring Done | IMG_0171
5 | January | 2024 | SVG | Temporary Storage Shed erected | IMG_0179
6 | January | 2024 | SVG | Earthwork retaining wall | IMG_0187
6 | January | 2024 | SVG | Damp Proof Course applied for sub structure wall | IMG_0194
9 | January | 2024 | SVG | Earthwork Excavation being done with JCB after delays due to rain | IMG_0209
| January | 2024 | SVG | Image showing slush/clay making work proceed at slow pace | IMG_0212
10 | January | 2024 | SVG | JCB Work stalled due to rain | IMG_0223
11 | January | 2024 | SVG | JCB Work resumed | upload_1704954398462
11 | January | 2024 | SVG | Plinth beam bar bending work | IMG_0228
11 | January | 2024 | SKL | Site Clearing Using JCB | upload_1704964012578
11 | January | 2024 | SKL | Site Clearing Using JCB (Including adjacent lands) | upload_1704971383584
12 | January | 2024 | SVG | Plinth Beam shuttering work being done | IMG_0235
12 | January | 2024 | SVG | Ready for concreting | IMG_0240
13 | January | 2024 | SVG | Concreting started in the early hours of 13th / abt 3 AM / Wanted to complete this milestone before Pongal break | IMG_0241
13 | January | 2024 | SVG | Concreting work going on | IMG_0246
13 | January | 2024 | SVG | Concreting work getting extended due to Traffic/Local issues / 8 35 am | IMG_0250
13 | January | 2024 | SVG | Concreting going on | IMG_0253
| January | 2024 | SVG | Concreting completed by 1030 am | IMG_0256
| January | 2024 | SVG
19 | January | 2024 | SVG | Deshuttering of plinth beams after pongal break | IMG_0279
19 | January | 2024 | SVG | Column starter work initiated | IMG_0290
20 | January | 2024 | SRF | Green net barricading work around the site | upload_1705723731788
| January | 2024 | SRF | Wood chips and coco peat purchased for site setback filling | upload_1705904690168
| January | 2024 | SRF | Compound wall raising and plastering at the Western boundary | upload_1705916298304
22 | January | 2024 | SRF | Site levelliing done using the purchase cocopeat/wood chips | upload_1705920676183
24 | January | 2024 | SRF | Setback filling using pruned tree branches / biomass | upload_1706090228922
25 | January | 2024 | SKL | Soil Testing work initiated | IMG_0306, IMG_0308
| January | 2024 | SKL | Water table at 2M height
| January | 2024 | SKL | Output of soil test at about 18 M | IMG_0317
| January | 2024 | SKL | Hardrock at abt 19-20M | IMG_0320
27 | January | 2024 | SRF | Site levelling work | upload_1706328695219
30 | January | 2024 | SVG | Plinth beam work / extension being done | IMG_0336
31 | January | 2024 | SVG | Column concreting being done at stilt level | IMG_0342
31 | January | 2024 | SVG | Column shoe marking work was done
1 | February | 2024 | SVG | Column box was installed
5 | February | 2024 | SVG | Damp proof course being done for remaining sections | IMG_0373
7 | February | 2024 | SRF | Site Levelling being done | upload_1707279363329
8 | February | 2024 | SVG | Earthwork excation using JCB for Sump | IMG_0399
9 | February | 2024 | SVG | Manual dressing done due to groundwater seepage | IMG_0408
10 | February | 2024 | SVG | Sump base slab concreting | IMG_0424
11 | February | 2024 | SVG | Sump side blockwork (1 side formwork) being done | IMG_0434, IMG_0437, IMG_0445
13 | February | 2024 | SVG | Dampproof / Waterproofing being done on sump outside wall | IMG_0449
14 | February | 2024 | SVG | Sump RCC wall barbending work | IMG_0453
| February | 2024 | SVG | Additional steel near sump inlet | IMG_0463
15 | February | 2024 | SVG | Shuttering being fixed for sump | IMG_0466
16 | February | 2024 | SVG | Additional Retaining wall around sump being constructed | IMG_0471
| February | 2024 | SVG | First flight of staircase - rebars being placed | IMG_0472
16 | February | 2024 | SVG | Sump formwork finalisation | IMG_0474
| February | 2024 | SVG | Sump formwork - rework / complete dismantling due to insufficient cover blocks | IMG_0482
17 | February | 2024 | SVG | Cover blocks added / confirmation to procced | IMG_0485
18 | February | 2024 | SVG | RMC for Staircase and Sump confirmed for start by 4AM | IMG_0488
| February | 2024 | SVG | Concreting going on | IMG_0491, IMG_0492
| February | 2024 | SVG | Concreting completed by 630 am | IMG_0493, IMG_0495
19 | February | 2024 | SVG | Formwork stripping done | IMG_0511
19 | February | 2024 | SRF | Additional wood chips purchase | upload_1708323085658, upload_1708401931413
19 | February | 2024 | SKL | Site boundary measurement along with adjacement land owners planned at 4PM /
20 | February | 2024 | SKL | Soil consolidation work | IMG_0521
| February | 2024 | SVG | Sump top slab centering work intiated | IMG_0523
| February | 2024 | SVG | Rebar placing work in progress | IMG_0531
21 | February | 2024 | SRF | Bhoomi Poojai annoucement board being erected at site | upload_1708526133610
22 | February | 2024 | SVG | Sump top slab concreting work | IMG_0550, IMG_0552
23 | February | 2024 | SVG | Curing work for sump top slab | IMG_0553
| February | 2024 | SVG | Brick steps being constructed | IMG_0562
26 | February | 2024 | SVG | Site barricade work being done | IMG_0570, IMG_0574
28 | February | 2024 | SKL | Site boundary/reference marks being kept | IMG_0579, IMG_0580, IMG_0581, IMG_0582, IMG_0584
29 | February | 2024 | SKL | Site work for Temporary EB connection | IMG_0588
1 | February | 2024 | SVG | First floor beam centering work started | IMG_0589
5 | February | 2024 | SVG | Formwork/Centering work going on | IMG_0595
5 | February | 2024 | SKL | Temporary EB Panel board compelted | IMG_0597, IMG_0604
7 | February | 2024 | SRF | Borewell work initiated | upload_1709789158354
| February | 2024 | SRF | Sand layer observed till about 25 feet | 1709805359179
| February | 2024 | SRF | The 60' depth of the bore well was accomplished today and further work scheduled/continued tomorrow.
? | ? | ? | SRF | CHECK WHEN WAS BOOMI POOJAI | ?
8 | March | 2024 | SVG | First floor slab formwork going on | IMG_0618
9 | March | 2024 | SVG |  | IMG_0628
12 | March | 2024 | SVG | Barbending(Steel cutting work) in progress for first floor slab / stilt roof | upload_1710235435797
| March | 2024 | SRF | Project approval board being erected at site | IMG_20240312_175000
13 | March | 2024 | SRF | Desiliting work done for the openwell | 1710303631008
14 | March | 2024 | SKL | EB Supply finally effected byh TNEB | IMG_20240314_173037
18 | March | 2024 | SVG | Beams being fabricated and kept in place in firstfloor slab | upload_1710733491990
19 | March | 2024 | SVG | Cover blocks placement | upload_1710840757195
21 | March | 2024 | SVG | Formwork Joint sealing work | IMG_0647
25 | March | 2024 | SVG | Pipe sleeves being placed to avoid break of beams latter during plumbing/drainage work | IMG_0655, IMG_0656
29 | March | 2024 | SVG | Electrical conduits being placed | IMG_0677
31 | March | 2024 | SVG | Concreting scheduled for first floor slab / Sunday night / starting around 1 am | IMG_0684
31 | March | 2024 | SVG | Concreting started | IMG_0685, IMG_0689
| March | 2024 | SVG | Concreting completed by 6am | upload_1711843712342, upload_1711843763832, 20240331_054904, IMG_0707
1 | April | 2024 | SVG | Curing initiated | IMG_0709
23 | April | 2024 | SVG | Formwork stripping initiated | IMG_0813
25 | April | 2024 | SVG | First floor column marking/shoe work/Starter concrete initiated | IMG_0834
27 | April | 2024 | SVG |  | IMG_0846
27 | April | 2024 | SVG | All formwork for slab removed | IMG_0849
30 | April | 2024 | SVG | Staircase brickwork | IMG_0863
2 | May | 2024 | SVG | First floor column rebar work started | IMG20240502165658
4 | May | 2024 | SVG | Column formwork in place | IMG_0973
| May | 2024 | SVG | Column conreting work started / Recron3s fiber being added to all concrete for crack control | IMG_0974, IMG_0975
6 | May | 2024 | SVG | Column concreting for remaining coluymns | IMG_0980
7 | May | 2024 | SVG | Curing for columns | IMG_0981
14 | May | 2024 | SVG | Formwork begins for first floor roof | IMG20240514130353, IMG20240514151959
16 | May | 2024 | SKL | New transformer post was fixed in near site frontage | IMG_1006
17 | May | 2024 | SRF | Plantation work | 1715921015107
18 | May | 2024 | SVG | Formwork/Staging/Props kept in place for first floor roof | IMG20240518101248
18 | May | 2024 | SRF | Manure filling and pruning/maintenance for all plants/trees planted | upload_1716023555133, upload_1716178458255
20 | May | 2024 | SVG | Brick steps being constructed / first floor flight | IMG20240520103345
27 | May | 2024 | SVG | Front beam work over compound wall | IMG_1060
29 | May | 2024 | SVG | Beams being fabricated and kept in place in secondfloor slab | IMG_1073, IMG20240529173519
31 | May | 2024 | SVG | Formwork Joint sealing work / First floor roof | IMG_1085
3 | June | 2024 | SVG | Earthing point installed | IMG_1098, IMG_1097
4 | June | 2024 | SVG | Conduit pipes being placed | IMG20240604162000
7 | June | 2024 | SVG | Concreating planned for midnight of 7th June for first floor roof | IMG_1109
| June | 2024 | SVG | Nitobond being applied- Checmical to have a strong bond of previous column to currently poured concreted | 1717709480285
| June | 2024 | SVG | Fosroc Conplast Crystalline - Crustalline waterproofing admixture being added to concrete | 1717710089955
7 | June | 2024 | SVG | Concreting started by 330am | 1717710858472
| June | 2024 | SVG | Quality control - Cubes being casted for testing | 1717714671680
| June | 2024 | SVG | Photo showing addition of Reliance Recron 3s - fiber reinforcement to concrete | IMG_20240607_063815, IMG_20240607_063834
| June | 2024 | SVG | Seweage pipes protected with concrete / Concreting completed by 730am | upload_1717726618000
8 | June | 2024 | SVG | Drainage chamber work being done | IMG_1119
10 | June | 2024 | SKL | Scaffolding work at site being done | 1717994025987, IMG_20240610_160915
10 | June | 2024 | SRF | Borewell submersible motor being installed | 1717996277371
11 | June | 2024 | SVG | Deshutteing of beam sides being done | 1718078212616
13 | June | 2024 | SVG | Drainage chamber work being done | IMG_1198, IMG_1204
14 | June | 2024 | SVG | Debris being moved offsite | IMG20240614152143
18 | June | 2024 | SKL | Watchmen shed being erected | IMG_1231
19 | June | 2024 | SKL | Site visit scheduled by Corporation AEE Mrs Geetha on 20 June 2024 for Site Inspection pertaining to our building plan submission
20 | June | 2024 | SVG | Staircase brickwork/Second floor flight | IMG_1244
24 | June | 2024 | SVG | Column starter work initiated for second floor columns | IMG_1265
26 | June | 2024 | SVG | Drainage chamber work being done | IMG20240626110842
27 | June | 2024 | SVG | Drainage chamber work being done / Manhole cover placed | IMG20240627150417
27 | June | 2024 | SVG | Second floor column formwork | IMG_1284
28 | June | 2024 | SVG | Second floor column concreting / Note - recron 3s being added | IMG_1291
29 | June | 2024 | SVG | Column formwork stripped and ready for curing compond application | IMG20240629095755
29 | June | 2024 | SVG | Curing compound being added | IMG20240629130037,IMG20240629130048
1 | July | 2024 | SVG | For remaining columns - Second floor column concreting / Note - recron 3s being added | IMG20240701153825, IMG20240701153821
2 | July | 2024 | SVG | Curing compound appllciation along with Hessian covering after formwork stripping | IMG20240702113735, IMG20240702112748
5 | July | 2024 | SVG | For taking care of minor honeycombing - Pressure grouting is being done instead of traditional plastering patchup | 1720155058251, 1720156532204
6 | July | 2024 | SVG | Damp proof course being done for planter box in stilt floor to take care of seepage | IMG_1330, IMG_1329
8 | July | 2024 | SVG | Concreting for 2nd floor staircase slab | IMG_1332
9 | July | 2024 | SVG | Consolidation of ground using course aggregatge | IMG_1341, IMG_1342
9 | July | 2024 | SVG | Second floor roof / formwork started | IMG_1343
10 | July | 2024 | SVG | Planter boxed strengtned using steel mesh | IMG_1349, IMG_1350
11 | July | 2024 | SVG | Hacking for stilt ceiling started for subsequent plastering work | IMG_1352
11 | July | 2024 | SVG | Brickwork for second floor flight/staircase | IMG_1355
15 | July | 2024 | SVG | Planter box plastering work | upload_1721016294242
18 | July | 2024 | SVG | Centering/staging work going on | IMG_1382
22 | July | 2024 | SVG | Steel being used for second floor roof work / CRS (Corrosion resistant steel) has been mandated as standard specification from this stage | IMG_1395
23 | July | 2024 | SVG | Formwork / gap sealing | IMG20240723120206
23 | July | 2024 | SVG | Beam being fabricated and kept in place | IMG_1401, IMG_1407
25 | July | 2024 | SVG | Rainwater chamber completed | IMG20240725180401
29 | July | 2024 | SVG | Electrical conduits being placed | IMG20240729145059, IMG20240729145108
29 | July | 2024 | SVG | Plumbing sleeves being placed to avoid beam cutting/breaking latter | IMG20240729145138, IMG20240729145152
31 | July | 2024 | SVG | RCC Ramp being constructed (Reinforcement being placed) | IMG_1452, upload_1722406796071
31 | July | 2024 | SVG | Stilt roof Plastering being done | IMG20240731104121
2 | August | 2024 | SVG | Concreting Scheduled fo 2 August 2024 / Midnight | IMG_1474
2026-08-03 | August | 2024 | SVG | Cocnreting started by around 3AM due to Transit mixing arriing late to site / Crystalline waterproofing admixture, Recron 3s fibers and other admixtures being added | 1722634427471, 1722634475751, upload_1722638884740
| August | 2024 | SVG | QC - Cubes being casted for testing | 1722635545413
| August | 2024 | SVG | Concreting work going on / 415 am | IMG_1477, IMG_1484, IMG_20240803_055355
4 | August | 2024 | SVG | Concreting completed by 8am and curing/ponding work started | IMG_1485
5 | August | 2024 | SVG | RCC Ramp Concreting | IMG20240805105126, IMG20240805121710, IMG_1488
6 | August | 2024 | SVG | Stilt roof Plastering being done | IMG20240806145940
7 | August | 2024 | SKL | Awaiting for joint inspection at site with owners regarding boundary line fixing | IMG_1494
10 | August | 2024 | SVG | External plastering work at stilt level | IMG20240810103021
14 | August | 2024 | SVG | External plastering work at stilt level | IMG_20240814_163156
20 | August | 2024 | SVG | Sump waterproofing and leakage testing being done | IMG_1529
22 | August | 2024 | SVG | Sump leakage test completed and injection grouting completed | IMG-20240821-WA0002
31 | August | 2024 | SVG | Formwork stripping and reproping being done | IMG20240831102641
2 | September | 2024 | SVG | Column starter being done | IMG20240902124249
6 | September | 2024 | SVG | Column concreting | IMG_20240906_093656
9 | September | 2024 | SVG | All columns completed and curing compound being applied | IMG20240909103455, IMG20240909152143
| September | 2024 | SVG | Sump plastering being done | IMG_1719
13 | September | 2024 | SVG | Column steel work initated for next level | IMG_1732
13 | September | 2024 | SVG | Slab staging/formwork started for terrace floor | IMG_1734
14 | September | 2024 | SVG | Ceiling plastering at stilt nearing completion | IMG20240914155248
16 | September | 2024 | SVG | Curing compond appliued for sump plastering work | IMG20240916102102
24 | September | 2024 | SVG | Terrace staircase / flight slab concreting | IMG_1787
25 | September | 2024 | SVG | Brickwork for third floor flight/staircase | IMG_1790
3 | October | 2024 | SVG | Beam being fabricated and kept in place | IMG_1860, IMG_1864
4 | October | 2024 | SRF | JCB/Earthwork for SUMP started | 1728013487588, IMG_20241004_100712, IMG_20241004_123420, IMG_1868
5 | October | 2024 | SRF | Earthwork for sump progressing | 1728100356199
| October | 2024 | SRF | PCC for sump base | 1728126635774
8 | October | 2024 | SVG | Rebars in place for terrace slab | IMG20241008103636
8 | October | 2024 | SRF | Brickwork for bottom 4 ft of sump formwork | 1728367303048, IMG_20241008_154733
| October | 2024 | SRF | Sump rebar fabrication work | IMG_20241008_154721
| October | 2024 | SRF | Reinforcement marking | 1728385975592
9 | October | 2024 | SRF | Placement of Geotextile around brickwall/formwork to prevent root ingress from nearby trees | 1728446771616
9 | October | 2024 | SVG | Electrical conduits being placed | IMG20241009103535, IMG20241010153019
9 | October | 2024 | SRF | Rebar fabraication and placement for sump rcc walls | IMG_20241009_150600
10 | October | 2024 | SRF | Concreting for Sump Base beams started | IMG_20241010_153159, 20241010_151808, 20241010_153847, IMG_20241010_161609
| October | 2024 | SRF | Concreting completed by 8PM | 20241010_200856
11 | October | 2024 | SVG | Concreting for third roof schedule to start by midnight / Delayed due to rain / Started by 130am | IMG_1891
| October | 2024 | SVG | IMG_1894 | waterproofing admixtures being added
| October | 2024 | SVG | Concreting going on | upload_1728594599007, upload_1728599588887
| October | 2024 | SVG | Concreting paused / delayed due to rain and vehicle breakdown
| October | 2024 | SVG | Restarted by 6.30am | IMG20241011062545
| October | 2024 | SVG | PCC concreting for stilt floor was done and concreting was finally completed by 9am | upload_1728615432306
14 | October | 2024 | SVG | Curing and ponding | IMG20241014101621
15 | October | 2024 | SVG | Rainwater / flood control effectvely working around the neighbour hood during intense pour of North East Monsoon rains | IMG_2062
17 | October | 2024 | SRF | Sump totally flooded due to rain | upload_1729136734518
18 | October | 2024 | SRF | Sump RCC wall barbending work | upload_1729155524196, IMG_20241018_105940
19 | October | 2024 | SRF | Swellable waterstop being placed along all sump construction joints | 1729308634456
| October | 2024 | SRF | Waterproof sealent in plcae at pipe inlets | 1729312456436
| October | 2024 | SRF | Formwork in palce for concreting | upload_1729314956016
| October | 2024 | SRF | Concreting schedule and started on time | IMG20241019173255
| October | 2024 | SRF | Admixtures (Recron, Crystalline waterp[roofing) being added | upload_1729339542241
| October | 2024 | SRF | Concreting for summp rcc walls going on | upload_1729340468666
| October | 2024 | SRF | QC - Cubes being casted for testing | upload_1729345761068
22 | October | 2024 | SKL | Site cleared | IMG_2144, IMG_2153
23 | October | 2024 | SRF | Curing compond applied for sump | 1729680333842
25 | October | 2024 | SKL | Soak pit for temporary toilet constructed | IMG20241025114520
26 | October | 2024 | SKL | Site levelling work / readying for Bhoomi Poojai | IMG_2191, IMG_2204, IMG20241027174958
27 | October | 2024 | SKL | Bhoomi Poojai done (CHECK)
28 | October | 2024 | SKL | Borewell work initiated | IMG_2229, IMG_2232, IMG_2236
29 | October | 2024 | SRF | Concrete rings for plant protection | 1730174827631
29 | October | 2024 | SRF | Concreting for sump top slab | upload_1730189417610
5 | November | 2024 | SVG | Formwork stipping done | IMG_2530
6 | November | 2024 |  | Column Starter constructed | IMG20241106154104
7 | November | 2024 | SKL | Borewell work completed / final depth 325 feet | IMG20241107101638
8 | November | 2024 | SRF | Scaffolding work at site being done | upload_1731060698705
9 | November | 2024 | SRF | Deshuttering of sump top slab | upload_1731142224951
11 | November | 2024 | SVG | Column concreting for top level/headroom at terrace | IMG_2545, IMG_2548
14 | November | 2024 | SVG | Headroom formwork started | IMG_2555
20 | November | 2024 | SVG | Headroom rebar work | IMG20241120095412
21 | November | 2024 | SVG | Concreting completed and curing compound applied | IMG20241121094300, IMG20241121123840
22 | November | 2024 | SRF | Backfilling around sump | upload_1732251226462
| November | 2024 | SRF | Plastering of openwell | 1732260416169
| November | 2024 | SRF | Creeper net kept in place at North West boundary area | upload_1732265148455
23 | November | 2024 | SRF | Dust barrier / Greennet being placed along western boundary | upload_1732352010268
28 | November | 2024 | SVG | Blockwork in lift shaft going on | IMG20241128151438
29 | November | 2024 | SVG | Column marking for lift room | IMG20241129162523
2 | December | 2024 | SVG | Terrace parapet wall work intiation / Note SBR Latex polyer being applied as bond coat and waterproofing use along with glass fibernet application | IMG20241202114827, IMG20241202115419, IMG_2654
4 | December | 2024 | SVG | Parapet works | IMG20241204125431
7 | December | 2024 | SKL | Borewell submersible motor being installed | IMG20241207114542, IMG_2676, IMG20241207171340
10 | December | 2024 | SKL | Temporary toilet constructed | IMG_2680
11 | December | 2024 | SVG | Machine roof beams fabricated and placed | IMG_2696
13 | December | 2024 | SVG | Concreting for machine room roof | IMG_2702
17 | December | 2024 | SVG | Terrace features being constructed | IMG_2717
18 | December | 2024 | SVG | Parapet and edge blockwork being done | IMG_2724, IMG_2721
19 | December | 2024 | SRF | Pilecap locations physically checked at site for tree interferance | 1734598759579
20 | December | 2024 | SRF | Site pile cap marking being done | IMG_20241220_112047
27 | December | 2024 | SRF | RCC rings being placed as protective measure against upcoming pile work / pile slush | 1735274016765
30 | December | 2024 | SRF | Deep buring of metrowater inlet pipes started | IMG_20241230_161846
31 | December | 2024 | SRF | Pile and pile cap drawings issued by consultant team

## Sheet2
Karunakaran ( circle secretary) | SVB | 97101 88001 | 10 | Feb | 2024
bala murugan ( sheet welder ) |  | 97890 44830 | 28 | March | 2024
Balamurugan SI to Writer Traffic Police Vadapalani |  | 9944236278 | 8 | Oct | 2024